## AICA Marketing Calendar
AICA Capstone Project & Marketing Activities Calendar (2026)
Marketing Elements & Deliverables | Channels | W5 (6/23) | W6 (6/30) | W7 (7/7) | W8 (7/14) | W9 (7/21) | W10 (7/28) | W11 (8/4) | W12 (8/11)
PHASE 1: PRE-LAUNCH SETUP & PLANNING (W5)
Goal: Configure recording hardware, establish hosting and monetization portals, set up social accounts, and pre-record a 2-episode buffer.
Submit formal Capstone Project Plan (June 23) | Brightspace Portal (Academic)
Configure USB cardioid microphones and Audacity noise parameters | Internal Setup (Hardware/Software)
Set up Spotify for Podcasters & Buzzsprout hosting portals | Spotify / RSS Distribution
Configure Patreon Premium Lab profile and subscription tiers ($4.99/$9.99) | Patreon Platform
Register TikTok, YouTube Shorts, and Xiaohongshu marketing accounts | TikTok, YouTube, Xiaohongshu
Pre-record Podcast Trailer, Episode 1, and Episode 2 | Audacity / cardiod microphones
PHASE 2: LAUNCH & RELEASE (W6)
Goal: Release podcast trailer, launch Spotify channel, establish Patreon Starter Tier, and distribute short-form promo vertical video campaigns.
Release Podcast Trailer & Episode 1 ('The AI Gap') | Spotify / Apple Podcasts
Publish Patreon Component 1: ATS-Friendly Resume Templates (Xu Ning profile) | Patreon Starter Tier ($4.99)
Pitch featured student article to Editor of Daily Trojan | PR / Press Outreach
Launch TikTok / YouTube vertical shorts & LinkedIn campaigns (Ongoing) | TikTok, YouTube Shorts, LinkedIn
Share Episode 1 link in Marshall Discord & WeChat group chats | WeChat, Discord Group Chats
Pre-record Episode 3 ('Chloe's Cold Text Autopsy') | Audacity / Team microphones
PHASE 3: ACTIVE OPERATIONS & MID-CAMPAIGN (W7)
Goal: Maintain weekly podcast releases, upload advanced Patreon prompt vaults, SCA student lounge promos, and Marshall club newsletter pitches.
Release Episode 2 ('ATS Demystified') & Component 2 (ATS Prompts) | Spotify / Patreon Professional ($9.99)
Release Episode 3 & Component 3 (3-Sentence Outreach Vault) | Spotify / Patreon Starter ($4.99)
Promote the free ATS resume template to USC Cinema (SCA) student groups | SCA Student Lounges / WeChat
Partner with student club presidents & pitch newsletter features | USC Marshall Student Clubs WeChat/Discord
Pre-record Episode 4 ('Rohan Sponsor Search') & Episode 5 ('Case & UX') | Audacity / Team microphones
PHASE 4: FINAL CAMPAIGNS & TARGET PROMO (W8)
Goal: Launch sponsor query scaffolds, target international engineering students, and complete all core MVP assets.
Release Episode 4 ('Rohan's Sponsorship Search') & Episode 5 ('Case Prep & UX') | Spotify / Apple Podcasts
Publish Patreon Component 4 (Visa Query Scaffolds) & Component 5 (UX Portfolio Guide) | Patreon Professional Tier ($9.99)
Promote Perplexity Visa sponsor query templates across USC Viterbi networks | Viterbi WeChat & Discord Groups
Share Perplexity search query guides on Xiaohongshu (Rednote) | Xiaohongshu (Rednote)
Complete all core MVP assets (5 podcast episodes and 5 Patreon components) | Spotify / Patreon
PHASE 5: SUBMISSION & QA (W9)
Goal: Execute final audio quality checks, package deliverables, submit project MVP, and launch during class.
Submission preparation, final audio QA & launch documentation | Internal Quality Control
Submit completed MVP podcast series and Patreon logs | Brightspace Portal (due July 21)
Post final social wrap-up clips & analytics hooks | TikTok, YouTube Shorts, LinkedIn
Live launch & project demonstration in class | DSM 596 Classroom
PHASE 6: POST-LAUNCH EVALUATION & PRESENTATION (W10-W12)
Goal: Analyze Spotify & Patreon dashboards, evaluate SMART goals, draft presentation slides, and deliver final capstone presentation.
Collect and compile Spotify & Patreon analytics (MRR/Downloads/CTR) | Spotify for Podcasters, Patreon
Compare performance metrics against SMART validation goals | Analytics Report Dashboard
Draft 15-minute final presentation slides (W10 Draft / W11 Finalize) | PowerPoint / Google Slides
Deliver final Capstone Presentation in class (due August 11) | DSM 596 Classroom